## Sheet1
Task Description | Start Date | Duration (approx.) | End Date | Completed | October | November | December | January | February | March | April | May | June
Milestone 1 | 08.10.19 | 2 months | 03.12.19 | [10 empty] | Milestone 1 | Not Completed
Milestone 2 | 03.12.19 | 2 months | 04.02.20 | [10 empty] | Milestone 2 | Completed
Milestone 3 | 04.02.20 | 2 months | 07.04.20 | [10 empty] | Milestone 3 | Duration
Milestone 4 | 07.04.20 | 1 month | 05.05.20 | [10 empty] | Milestone 4
Milestone 5 | 05.05.20 | 1 month | 02.06.20 | [10 empty] | Milestone 5
App GUI Prototype | 15.10.19 | 3 weeks | 05.11.19
Searching Algorithm | 12.11.19 | 4 weeks | 10.12.19
App GUI Full | 05.11.19 | 3 months | 04.02.20
Database Connection | 28.10.19 | 2 weeks | 10.11.19
Installations | 06.10.19 | 1 week | 13.10.19
Design constructions | 22.10.19 | 1 week | 29.10.19
Proof of concept | 29.10.19 | 2 weeks | 12.11.19
Major Contingencies | 05.11.19 | 3 weeks | 19.11.19
Android Store implementation | 05.05.20 | 2 weeks | 19.05.20
Document Download Option | 22.01.20 | 2 weeks | 05.02.20
Document Manipulation | 07.04.20 | 3 weeks | 28.04.20
Storage of User History | 01.03.20 | 2 weeks | 14.03.20
Storage of User Settings | 14.03.20 | 3 weeks | 07.04.20